## ITP
Inspection & Test Plan (ITP) — Construction QA/QC
Project: |  |  |  | Client: |  |  |  | ITP No.:
Discipline: |  |  |  | Revision: |  |  |  | Date:
Reference Specifications: |  |  |  | Codes:
Legend: H = Hold Point ¦ W = Witness ¦ R = Review of records ¦ M = Monitor ¦ S = Surveillance ¦ I = Information only
# | ITP Code | Activity / Inspection Item | Method | Acceptance Criteria | Reference Document | Frequency | Contractor | Sub-Contractor | Client / TPI | Records
01 | ITP-001 | Material receiving inspection (MTR review) | Document review + visual | Per PO / Spec. + EN 10204 3.1 | ASME II / EN 10204 | Each heat / lot | M | M | R | MRR + MTR
02 | ITP-002 | Welding Procedure Specification (WPS) review | Doc review | ASME Section IX qualified | ASME IX / WPS | Each WPS | R | — | R | WPS + PQR
03 | ITP-003 | Welder qualification verification | Doc review | ASME Section IX QW-300 | ASME IX | Each welder | M | — | R | WPQ records
04 | ITP-004 | Joint fit-up inspection | Visual + measurement | Per drawing + WPS tolerances | Drawing / WPS | Each joint | M | M | W | Fit-up report
05 | ITP-005 | Pre-heat verification | Temperature measurement | Min per WPS / Code | WPS / ASME B31.3 | Each joint when applicable | M | M | S | Pre-heat log
06 | ITP-006 | Visual inspection of welds (VT) | VT per ASME V Article 9 | Per code (ASME Section VIII / B31.3) | ASME V / VIII / B31.3 | 100% of welds | M | M | W/R | VT report
07 | ITP-007 | Magnetic Particle Testing (MT) | Yoke / prod / continuous | ASME VIII Appendix 6 | ASME V Article 7 | Per project spec. | M | M | R | MT report
08 | ITP-008 | Liquid Penetrant Testing (PT) | Solvent removable / water-washable | ASME VIII Appendix 8 | ASME V Article 6 | Per project spec. | M | M | R | PT report
09 | ITP-009 | Ultrasonic Testing (UT) | Manual / PAUT | ASME VIII Appendix 12 / 4 | ASME V Article 4 / 5 | Per project spec. | M | M | W/R | UT report
10 | ITP-010 | Radiographic Testing (RT) | Gamma / X-ray | ASME VIII Appendix 4 | ASME V Article 2 | Per project spec. | M | M | W/R | RT film/DR + report
11 | ITP-011 | Post-Weld Heat Treatment (PWHT) | Heat treatment | Per WPS / Code | ASME VIII UCS-56 | Each cycle | H | M | W | PWHT chart + record
12 | ITP-012 | Hardness Testing | Brinell / Vickers | ASME B31.3 Table 331.1.1 | ASME B31.3 | Per spec. | M | M | R | Hardness report
13 | ITP-013 | Positive Material Identification (PMI) | OES / XRF | Per material spec. | API 578 | 100% / sampling | M | M | R | PMI report
14 | ITP-014 | Dimensional / final visual inspection | VT + measurement | Per drawing tolerances | Drawing | 100% of assemblies | M | M | W | Dimensional report
15 | ITP-015 | Pressure Test (hydrotest / pneumatic) | Hydro / pneumatic | Per code | ASME VIII UG-99 / B31.3 §345 | Each system | H | M | W | Pressure-test record
16 | ITP-016 | Surface preparation & painting | VT + thickness | Per spec. | SSPC / NACE | Each coat | M | M | S/R | Coating report
17 | ITP-017 | Final documentation review | Doc review | Per project QA plan | Project QA Plan | Project close | R | — | R | Final dossier / MRB
ITP Approval
Role | Name | Position / Cert | Signature | Date | Comments | — | — | — | — | —
Contractor QC Manager
Welding Engineer
Sub-Contractor QC
Client Project Manager
TPI / Third Party
© Atlantis NDT — Free template. Customize for your specific application. Demo: info@atlantisndt.com ¦ atlantisndt.com